## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect Azure compute and storage usage data across regions so that historical demand patterns can be analyzed for forecasting. | MUST HAVE | Azure usage dataset availability | Backend Team | 3- Completed
Sprint 1 | Sprint 1 | US002 | As a data analyst, I want to explore and analyze the collected datasets to identify trends and anomalies so that useful insights can support feature engineering. | MUST HAVE | Raw datasets | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US003 | As a data engineer, I want to clean and preprocess the collected datasets by handling missing values and standardizing formats so that the data becomes consistent for analysis. | MUST HAVE | Raw datasets | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US004 | As a data scientist, I want to perform feature engineering such as lag variables, seasonality indicators, and usage spikes so that the dataset can capture demand patterns effectively. | MUST HAVE | Cleaned dataset | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US005 | As a data scientist, I want to transform and structure the dataset into a model ready format with consistent time granularity so that machine learning models can be trained efficiently. | MUST HAVE | Feature engineered dataset | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US006 | As an ML engineer, I want to train forecasting models such as ARIMA and XGBoost using historical usage data so that future Azure service demand can be predicted accurately. | MUST HAVE | Processed dataset | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US007 | As an ML engineer, I want to evaluate the trained models using metrics like MAE and RMSE so that the most accurate model can be selected for deployment. | SHOULD HAVE | Trained models | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US008 | As an ML engineer, I want to perform hyperparameter tuning for models like XGBoost so that forecasting accuracy can be improved. | SHOULD HAVE | Initial trained model | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US009 | As a DevOps engineer, I want to deploy the trained forecasting model into a production environment so that real time demand predictions can be generated. | MUST HAVE | Final trained model | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US010 | As a backend developer, I want to create APIs that deliver demand forecast results to the frontend dashboard so that predictions can be visualized in real time. | MUST HAVE | Trained model | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US011 | As a frontend developer, I want to create a dashboard that displays demand forecasts and capacity insights so that stakeholders can easily visualize predictions. | COULD HAVE | Backend APIs ready | Frontend Team | 3- Completed
Sprint 4 | Sprint 4 | US012 | As a frontend developer, I want to display forecast comparison graphs (actual vs predicted demand) so that users can easily understand model performance. | COULD HAVE | Backend API integration | Frontend Team | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Collect raw cloud capacity dataset and verify structure | 2025-02-05 | 2025-02-06 | Backend1 | Data Collection | 3- Completed | 4 | bar: Day 1 to Day 2
US002 | T2 | Handle missing values in dataset | 2025-02-06 | 2025-02-08 | DataEngineer1 | Data Cleaning | 3- Completed | 6 | bar: Day 2 to Day 4
US003 | T3 | Remove duplicate records and inconsistent entries | 2025-02-07 | 2025-02-08 | DataEngineer2 | Data Cleaning | 3- Completed | 3 | bar: Day 3 to Day 4
US004 | T4 | Convert timestamp column to datetime format | 2025-02-09 | 2025-02-09 | DataEngineer1 | Data Preprocessing | 3- Completed | 2 | bar: Day 4
US005 | T5 | Perform exploratory data analysis on usage patterns | 2025-02-10 | 2025-02-12 | DataScientist1 | Data Analysis | 3- Completed | 5 | bar: Day 5 to Day 7
US006 | T6 | Standardize region and service type labels | 2025-02-12 | 2025-02-13 | DataEngineer2 | Data Transformation | 3- Completed | 3 | bar: Day 6 to Day 7
US007 | T7 | Finalize cleaned dataset for feature engineering | 2025-02-14 | 2025-02-16 | DataScientist1 | Data Validation | 3- Completed | 3 | bar: Day 7 to Day 8
SPRINT 2 BACKLOG
US008 | T8 | Plan feature engineering strategy for forecasting dataset | 2025-02-20 | 2025-02-21 | DataScientist1 | Feature Planning | 3- Completed | 3 | bar: Day 1 to Day 2
US009 | T9 | Create time based features (year, month, quarter, week) | 2025-02-21 | 2025-02-23 | DataEngineer1 | Feature Engineering | 3- Completed | 4 | bar: Day 2 to Day 4
US010 | T10 | Generate lag features for historical demand analysis | 2025-02-23 | 2025-02-25 | DataScientist1 | Feature Engineering | 3- Completed | 5 | bar: Day 3 to Day 5
US011 | T11 | Create rolling mean and rolling standard deviation features | 2025-02-25 | 2025-02-27 | DataEngineer2 | Feature Engineering | 3- Completed | 4 | bar: Day 4 to Day 6
US012 | T12 | Calculate capacity utilization and growth rate indicators | 2025-02-27 | 2025-02-28 | DataScientist2 | Feature Engineering | 3- Completed | 3 | bar: Day 5 to Day 6
US013 | T13 | Detect demand spikes using statistical anomaly detection | 2025-02-28 | 2025-03-01 | DataScientist1 | Data Analysis | 3- Completed | 3 | bar: Day 6 to Day 7
US014 | T14 | Export final feature engineered dataset for model training | 2025-03-01 | 2025-03-02 | DataEngineer1 | Data Preparation | 3- Completed | 2 | bar: Day 7
SPRINT 3 BACKLOG
US015 | T15 | Prepare feature engineered dataset for model training | 2025-03-06 | 2025-03-07 | DataScientist1 | Data Preparation | 3- Completed | 3 | bar: Day 1 to Day 2
US016 | T16 | Train ARIMA forecasting model on demand dataset | 2025-03-07 | 2025-03-09 | DataScientist2 | Model Development | 3- Completed | 4 | bar: Day 2 to Day 4
US017 | T17 | Train XGBoost regression model for demand forecasting | 2025-03-09 | 2025-03-11 | ML Engineer1 | Model Development | Done | 5 | bar: Day 3 to Day 5
US018 | T18 | Perform hyperparameter tuning for XGBoost model | 2025-03-11 | 2025-03-13 | ML Engineer1 | Model Optimization | Done | 4 | bar: Day 4 to Day 6
US019 | T19 | Develop LSTM model for time series demand prediction | 2025-03-13 | 2025-03-15 | DataScientist1 | Deep Learning | Done | 6 | bar: Day 5 to Day 7
US020 | T20 | Evaluate model performance using MAE RMSE and R2 metrics | 2025-03-15 | 2025-03-16 | DataScientist2 | Model Evaluation | Done | 3 | bar: Day 6 to Day 7
SPRINT 4 BACKLOG
US021 | T21 | Select best performing model for deployment | 2025-03-20 | 2025-03-21 | ML Engineer1 | Model Selection | Done | 3 | bar: Day 1 to Day 2
US022 | T22 | Serialize trained XGBoost model and save as .pkl file | 2025-03-21 | 2025-03-22 | DataScientist1 | Model Packaging | Done | 2 | bar: Day 2
US023 | T23 | Design deployment workflow for forecasting pipeline | 2025-03-22 | 2025-03-24 | ML Engineer2 | System Design | Done | 4 | bar: Day 3 to Day 5
US024 | T24 | Plan Streamlit dashboard for demand forecast visualization | 2025-03-24 | 2025-03-26 | Frontend1 | UI Planning | Done | 4 | bar: Day 4 to Day 6
US025 | T25 | Prepare project documentation and evaluation reports | 2025-03-26 | 2025-03-28 | Team1 | Documentation | Done | 4 | bar: Day 5 to Day 7
US026 | T26 | Final project review and milestone validation | 2025-03-28 | 2025-03-30 | Team1 | Project Review | Done | 3 | bar: Day 6 to Day 7

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Working with incomplete or undocumented datasets | Created structured dataset and generated initial EDA report
Sprint 2 | Day 2 | Manual and inconsistent data cleaning methods | Produced cleaned and feature-engineered dataset ready for modeling
Sprint 3 | Day 1 | Training models without proper validation | Selected best-performing forecasting model after hyperparameter tuning
Sprint 4 | Day 2 | Delaying backend–frontend integration until the end | Successfully deployed forecasting API and built interactive dashboard

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-16 | Backend Team | Collect data and perform exploratory data analysis to identify demand trends | Working with incomplete or undocumented datasets | Collaborative data exploration and documentation | Created structured dataset and generated initial EDA report
2 | Sprint 2 | 2026-02-16 | 2026-03-02 | Backend Team | Implement data preprocessing pipeline and perform feature engineering such as lag features and seasonality indicators | Manual and inconsistent data cleaning methods | Automating preprocessing scripts for consistency | Produced cleaned and feature-engineered dataset ready for modeling
3 | Sprint 3 | 2026-03-02 | 2026-03-16 | Backend Team | Train forecasting models such as ARIMA and XGBoost and evaluate them using MAE and RMSE metrics | Training models without proper validation | Iterative model experimentation and performance comparison | Selected best-performing forecasting model after hyperparameter tuning
4 | Sprint 4 | 2026-03-16 | 2026-03-30 | Backend + Frontend Team | Deploy trained forecasting model, develop APIs for prediction delivery, and create dashboard for visualization of forecast results | Delaying backend–frontend integration until the end | Continuous integration and testing between backend APIs and frontend dashboard | Successfully deployed forecasting API and built interactive dashboard with forecast comparison graphs